COB640	ENGENHARIA CONCORRENTE: PERSPECTIVAS PARA O SETOR ESPACIAL/ CONCURRENT ENGINEERING: PERSPECTIVES FOR THE BRAZILIAN SPACE SECTOR

Flávio de Azevedo Corrêa Jr1,   Luis Gonzaga Trabasso2      &     Isak Kruglianskas3

1Instituto de Aeronáutica e Espaço, Centro Técnico Aerospacial, São José dos Campos - SP,   e-mail: flavio@ase2.iae.cta.br

2Instituto Tecnológico de Aeronáutica,   Centro Técnico Aerospacial,   São José dos Campos - SP,   e-mail: gonzaga@mec.ita.cta.br

3FEA /PACTo,  Universidade de São Paulo,  São Paulo - SP,  e-mail: ikruglia@usp.br

The development cycle of a satellite launch vehicle is a task that requires considerable maturity and commitment of the design team. The increasing complexity of the tasks involved and the frequent design changes do create the need for attempts to reduce the development cycle period as well as to implement their rational management. Although one may consider the aerospace industry as a highly developed one, it keeps its structure in a sequential manner, where the events quite often do not relate to each other, thus preventing the aerospace industry to benefit from effort and rework minimisation. This paper presents a retrospective analysis of the management and design tools recently used in the Brazilian aerospace projects and suggests the utilisation of some concurrent engineering tools which could enhance the performance and productivity of future projects.

Keywords: Concurrent engineering, Project management, Design teams, Design tools, Engenharia Simultânea.